## Weekly Gantt Chart Template
MONTHLY GANTT CHART
|  | Social Story |  | Group-20 |  |  |  | 2020-11-02 |  |  |  |  | 2021-07-01
|  | PROJECT NAME |  | OWNER |  |  |  | START DATE |  |  |  |  | END DATE
Project Description | Task ID | Task Name | Start | End | Progress | Date | MO01 | MO02 | MO03 | MO04 | MO05 | MO06 | MO07 | MO08 | MO09 | WK17 | WK17 | WK17
Social Story is an android based application. It is a social skills training learning application. Also it will help to learn basic mathematic operation and some important english words. It is specially designed for the children with ASD or other developmental disorders. This application created by the Group-20 of CSE department of STCET, 2021 batch under the guidance of Mr. Debashis Chakraborty sir. |  |  | Week | Week
| 01 | Requirement Analysis | MO01 | MO01 | 100% | 2020-11-02 | 1
| 01.01 | Identifying Problem | WK01 | WK01 | 100%
| 01.02 | Project Planning | WK01 | WK01 | 100%
| 01.03 | Resource Planning | WK02 | WK02 | 100%
| 01.04 | Literature Survey | WK03 | WK03 | 100%
| 01.05 | Phase Review | WK04 | WK04 | 100%
| 02 | Design | MO02 | MO02 | 100% | 2020-12-01 |  | 1
| 02.01 | Layout Design | WK01 | WK01 | 100%
| 02.02 | Resource Design | WK02 | WK02 | 100%
| 02.03 | Logo Design | WK03 | WK03 | 100%
| 02.04 | Feature Design | WK04 | WK04 | 100%
| 03 | Development | MO03 | MO07 | 100% | 2021-01-01 |  |  | 1 | 1 | 1 | 1 | 1
Remarks | 03.01 | Layout Development | MO03 | MO04 | 100% |  |  |  | 1 | 1
Weekly monitoring has been made to make sure the objectives are achieved. Improvement on the action plans shall be enhance along the way from time to time. | 03.02 | Resource Development | MO04 | MO04 | 100% |  |  |  |  | 1
| 03.03 | Backend Development | MO05 | MO07 | 100% | [5 empty] | 1 | 1 | 1
| 04 | Quality Assurance | MO08 | MO08 | 100% | 2021-06-01 | [7 empty] | 1
| 4.01 | System Testing | WK01 | WK01 | 100%
| 4.02 | Deploy | WK02 | WK02 | 100%
| 4.03 | Unit Testing | WK03 | WK04 | 100%
| 5 | Final Assessment | MO09 | MO09 | 100% | 2021-07-01 | [8 empty] | 1

## ©
© TemplateLab.com